## Sprint 06
G | AWD - Product Team
Sprint | 05 (09-SEP-2024 to 20-SEP-2024) |  | Day 1 (09/09/2024) |  |  |  | Day 2 (09/10/2024) |  |  |  | Day 3 (09/11/2024) |  |  |  | Day 4 (09/12/2024) |  |  |  | Day 5 (09/13/2024) |  |  |  | Day 6 (09/16/2024) |  |  |  | Day 7 (09/17/2024) |  |  |  | Day 8 (09/18/2024) |  |  |  | Day 9 (09/19/2024) |  |  |  | Day 10 (09/20/2024)
|  | Resource | Activity | Status | Completion % | Comments | Activity | Status | Completion % | Comments | Activity | Status | Completion % | Comments | Activity | Status | Completion % | Comments | Activity | Status | Completion % | Comments | Activity | Status | Completion % | Comments | Activity | Status | Completion % | Comments | Activity | Status | Completion % | Comments | Activity | Status | Completion % | Comments | Activity | Status | Completion % | Comments
|  | Sai Kiran | #Dev# Replicate the issue in the Lower environments. | In Progress |  |  | #Dev# Replicate the issue in the Lower environments. | In Progress |  |  | Preparing for the Access Holding Interview. | In Progress |  |  | Preparing for the Access Holding Interview. | Completed |  |  | #DEV# Working on SPM Logic app. |  |  |  | #DEV# Investigating on prod SPM Function App. | In Progress |  |  | Leave |  |  |  | #DEV# Investigating on CDR calls from DPC Application. | In Progress |  |  | #DEV# Investigating on CDR calls from DPC Application. | In Progress
|  | Vinay | #DEV# Working on Medici - DB Migration. | In Progress |  |  | #DEV# Working on Medici - DB Migration. | In Progress |  |  | #DEV# Working on SPM Logic app. | In Progress |  |  | #DEV# Working on SPM Logic app. | In Progress |  |  | #DEV# Working on SPM Logic app. |  |  |  | #DEV# Working on SPM Logic app. | In Progress |  |  | #DEV# Working on SPM Logic app. | Completed |  |  | #DEV# Working on internal application. | In Progress |  |  | Leave
[15 empty] | #DEV# Investigating and Resolving the Foreign Key exception. | Completed
|  | Thanusha | Learnings on Selenium with python. | In Progress |  |  | Leave |  |  |  | #QA# Going through the user stories and preparing sprint summary. | Completed |  |  | Learnings | In Progress |  |  | Learnings |  |  |  | Learnings | In Progress |  |  | #QA# Regression Testing on Winde application. | Completed |  |  | Learnings | In Progress |  |  | Learnings | In Progress
|  |  | #QA# Preparing Sprint Summary and Review PPT. | Completed
|  |  | Create sprint summary document for Sprint 05 | In Progress
|  | Sai Kiran | #Dev# Replicate the issue in the Lower environments. |  |  |  | Preparing for the Access Holding Interview. |  |  |  | Preparing for the Access Holding Interview. |  |  |  | #DEV# Working on SPM Logic app. |  |  |  | #DEV# Investigating on prod SPM Function App. |  |  |  | Leave |  |  |  | #DEV# Investigating on CDR calls from DPC Application. |  |  |  | #DEV# Investigating on CDR calls from DPC Application. |  |  |  | #DEV# Investigating on CDR calls from DPC Application.
|  | Vinay | #DEV# Working on Medici - DB Migration. |  |  |  | #DEV# Working on SPM Logic app. |  |  |  | #DEV# Working on SPM Logic app. |  |  |  | #DEV# Working on SPM Logic app. |  |  |  | #DEV# Working on SPM Logic app. |  |  |  | #DEV# Working on SPM Logic app. |  |  |  | #DEV# Working on internal application. |  |  |  | Leave |  |  |  | #DEV# Investigating on SPM issue.
|  | Thanusha | Leave |  |  |  | #QA# Going through the user stories and preparing sprint summary. |  |  |  | Learnings |  |  |  | Learnings |  |  |  | Learnings |  |  |  | #QA# Regression Testing on Winde application. |  |  |  | Learnings |  |  |  | Learnings |  |  |  | #QA# Investigating on SPM issue.
pron